## Sheet1
CIP_ID | Project_Name | Department | Asset_Category | Asset_Type | Phase | Phase_Status | Priority_Score | Fiscal_Year | Project_Start_Date | Project_End_Date | Capital_Cost | Operating_Cost_Annual | Funding_Availability | Primary_Funding_Source | Secondary_Funding_Source | Grant_Amount | Debt_Financing | Local_Match | Project_Manager | District_Region | Latitude | Longitude | X_Coordinate | Y_Coordinate | Description | Flood_Mitigation_Score | Sustainability_Score | Economic_Impact_Score | Social_Justice_Equity_Score | Risk_Mitigation_Score | Constructability_Score | Life_Cycle_Cost_Analysis | Benefit_Cost_Analysis | Regulatory_Compliance | Notes
CIP-0001 | Water Treatment Plant Expansion | Water Utility | Water Treatment | Treatment Plant | planning | In Progress | 5 | FY2026 | 2026-01-15 | 2030-12-31 | 12500000 | 320000 | Yes | General Obligation Bond | State Revolving Fund (SRF) | 0 | 12500000 | 0 | Jennifer Marsh | North District | 28.6158 | -81.2509 | -81.2509 | 28.6158 | Expand plant capacity from 8 MGD to 14 MGD to meet 2040 demand. | 2 | 3 | 5 | 3 | 5 | 3 | Yes | Yes | Safe Drinking Water Act | Phase 1 of 3
CIP-0002 | Sanitary Sewer Rehabilitation – Zone 4 | Wastewater | Collection System | Sewer Main | planning | Complete | 4 | FY2026 | 2026-02-01 | 2027-11-30 | 3200000 | 125000 | Yes | SRF Loan | Local Utility Revenues | 1500000 | 1700000 | 0 | Marcus Thompson | East District | 28.5428 | -81.1964 | -81.1964 | 28.5428 | CCTV and condition assessment of aging sewer mains. | 3 | 3 | 3 | 3 | 4 | 4 | Yes | Yes | Clean Water Act / NPDES | Phase 1 of 3
CIP-0003 | WWTP Nutrient Removal Upgrade | Wastewater | Wastewater Treatment | Treatment Facility | planning | In Progress | 5 | FY2026 | 2026-03-01 | 2032-06-30 | 18750000 | 450000 | Yes | General Obligation Bond | SRF Loan | 3000000 | 15750000 | 0 | Sarah Kim | Central | 28.5383 | -81.3792 | -81.3792 | 28.5383 | Evaluate BNR alternatives to comply with tighter effluent limits. | 2 | 3 | 4 | 3 | 5 | 3 | Yes | Yes | NPDES Permit Limit | Consent order deadline 2031
CIP-0004 | Main Street Corridor Reconstruction | Public Works – Roads | Transportation | Roadway | planning | Complete | 4 | FY2026 | 2026-01-01 | 2028-09-30 | 5600000 | 180000 | Yes | Federal Aid (STBG) | Local Motor Fuel Tax | 3360000 | 2240000 | 0 | David Nguyen | Downtown District | 28.5411 | -81.375 | -81.375 | 28.5411 | Corridor study, traffic analysis, and stakeholder outreach. | 3 | 3 | 4 | 3 | 3 | 4 | Yes | Yes | Local Ordinance / ADA | IDOT coordination required
CIP-0005 | Bridge No. 14 Replacement – Oak Ave | Public Works – Roads | Transportation | Bridge | planning | Complete | 5 | FY2026 | 2026-01-15 | 2028-12-31 | 4100000 | 100000 | Yes | Federal Aid (BIP) | County Capital Funds | 2870000 | 1230000 | 0 | Rachel Osei | West District | 28.5265 | -81.4892 | -81.4892 | 28.5265 | Condition assessment and type study for bridge replacement. | 5 | 2 | 4 | 3 | 5 | 4 | Yes | Yes | AASHTO / IDOT Standards | NBI rating 3 (poor)
CIP-0006 | Green Infrastructure – River District CSO | Stormwater | Stormwater Management | Stormwater | planning | In Progress | 4 | FY2026 | 2026-04-01 | 2031-03-31 | 7800000 | 225000 | Yes | EPA Green Project Reserve | Stormwater Utility Fees | 2000000 | 5800000 | 0 | Carlos Rivera | River District | 28.5299 | -81.3834 | -81.3834 | 28.5299 | Evaluate distributed GI alternatives to reduce CSO volume. | 5 | 5 | 3 | 4 | 4 | 3 | Yes | Yes | CSO Long Term Control Plan | LRT Phase 1
CIP-0007 | Substation 7 Modernization | Electric Utility | Electrical Infrastructure | Substation | planning | In Progress | 5 | FY2026 | 2026-02-15 | 2029-09-30 | 9200000 | 190000 | Yes | Revenue Bond | Utility Reserves | 0 | 9200000 | 0 | Lisa Park | South District | 28.4927 | -81.3657 | -81.3657 | 28.4927 | Replace aging substation equipment including transformer, breakers, and SCADA. | 2 | 3 | 5 | 2 | 5 | 4 | Yes | Yes | NERC Reliability Standards | Transformer end-of-life
CIP-0008 | Riverside Park Master Plan & Improvements | Parks & Recreation | Parks Infrastructure | Park | planning | Complete | 3 | FY2026 | 2026-01-01 | 2030-12-31 | 2850000 | 110000 | Yes | General Fund / Park District Grant | State Park Grant | 400000 | 2450000 | 0 | Tom Bradley | River District | 28.5558 | -81.3651 | -81.3651 | 28.5558 | Master plan and community engagement for park improvements. | 3 | 5 | 3 | 4 | 3 | 4 | Yes | Yes | Local Park Ordinance | Phase 1 of 3
CIP-0009 | Enterprise GIS & Asset Management System | Information Technology | Technology Infrastructure | Software / GIS | planning | Complete | 4 | FY2026 | 2026-01-01 | 2028-06-30 | 1950000 | 90000 | Yes | General Fund | Internal Technology Reserve | 0 | 1950000 | 0 | Amy Chen | All Departments | 28.5382 | -81.3791 | -81.3791 | 28.5382 | Enterprise GIS and CMMS integration to replace legacy systems. | 1 | 5 | 4 | 4 | 3 | 4 | Yes | Yes | Internal Operational Need | Replaces 3 legacy siloed systems
CIP-0010 | Public Safety Communications Tower | Public Safety | Communications | Communications Facility | planning | In Progress | 5 | FY2026 | 2026-03-01 | 2029-03-31 | 3450000 | 120000 | Yes | General Obligation Bond | Homeland Security Grant | 500000 | 2950000 | 0 | Chief Brian Hall | County-Wide | 28.4389 | -81.3164 | -81.3164 | 28.4389 | New tower for public safety communications coverage and reliability. | 3 | 3 | 5 | 3 | 5 | 4 | Yes | Yes | FCC Regulations | Replacing analog system
CIP-0011 | Natural Gas Distribution Main Replacement | Gas Utility | Gas Distribution | Gas Main | planning | In Progress | 4 | FY2026 | 2026-02-01 | 2028-09-30 | 4600000 | 140000 | Yes | Revenue Bond | Utility Reserves | 0 | 4600000 | 0 | Kevin Walsh | South District | 28.4685 | -81.3218 | -81.3218 | 28.4685 | Replace vintage cast iron and bare steel gas mains. | 3 | 2 | 4 | 2 | 5 | 4 | Yes | Yes | PHMSA / DOT 192 | DIMP priority segment
CIP-0012 | Operations & Maintenance Facility Renovation | Facilities Management | Buildings & Facilities | Government Building | planning | Complete | 3 | FY2026 | 2026-01-15 | 2030-06-30 | 6400000 | 175000 | Yes | General Obligation Bond | Capital Improvement Fund | 0 | 6400000 | 0 | Patricia Moore | Central | 28.5456 | -81.3519 | -81.3519 | 28.5456 | Renovation of aging operations and maintenance facility. | 2 | 3 | 3 | 3 | 3 | 4 | Yes | Yes | Local Building Code / ADA | 45,000 SF existing facility
CIP-0013 | Water Main Loop – Industrial Park | Water Utility | Water Distribution | Water Main | planning | Not Started | 3 | FY2030 | 2030-01-01 | 2033-12-31 | 5100000 | 125000 | Yes | Revenue Bond | Developer Contributions | 0 | 5100000 | 0 | Jennifer Marsh | Industrial District | 28.4822 | -81.1528 | -81.1528 | 28.4822 | Loop water main to improve fire flow and resiliency. | 5 | 3 | 5 | 2 | 4 | 4 | Yes | Yes | Fire Flow Requirements | Tied to industrial expansion plan 2029
CIP-0014 | Regional Biosolids Management Facility | Wastewater | Biosolids | Treatment Facility | planning | Not Started | 5 | FY2029 | 2029-01-01 | 2038-12-31 | 42000000 | 900000 | Yes | SRF Loan / Revenue Bond | Participating Utility Contributions | 5000000 | 37000000 | 0 | Sarah Kim | Regional | 28.6113 | -81.2105 | -81.2105 | 28.6113 | Regional biosolids processing facility for multiple utilities. | 2 | 4 | 5 | 3 | 5 | 3 | Yes | Yes | 40 CFR Part 503 | Involves 4 neighboring utilities
CIP-0015 | Smart Grid AMI Rollout – Full Territory | Electric Utility | Electrical Infrastructure | Smart Grid / AMI | planning | Not Started | 3 | FY2027 | 2027-01-01 | 2031-06-30 | 8300000 | 200000 | Yes | Revenue Bond | State Energy Efficiency Grant | 0 | 8300000 | 0 | Lisa Park | All Districts | 28.5569 | -81.2929 | -81.2929 | 28.5569 | AMI rollout with communications network and billing integration. | 1 | 5 | 4 | 4 | 3 | 4 | Yes | Yes | State Energy Efficiency Mandate | ~22,000 meters
CIP-0016 | Wastewater Pump Station 12 Upgrade | Wastewater | Pump Station | Pump Station | design | In Progress | 4 | FY2027 | 2027-05-01 | 2029-12-31 | 5200000 | 155000 | Yes | SRF Loan | Local Utility Revenues | 1000000 | 4200000 | 0 | Marcus Thompson | West District | 28.4922 | -81.2946 | -81.2946 | 28.4922 | Upgrade pumps, controls, standby power, and wet well improvements. | 3 | 3 | 4 | 3 | 5 | 4 | Yes | Yes | NPDES Permit / Reliability | Backup generator included
CIP-0017 | Downtown Flood Control Improvements | Stormwater | Flood Control | Drainage Infrastructure | design | In Progress | 5 | FY2027 | 2027-06-01 | 2032-12-31 | 9800000 | 240000 | Yes | Federal Grant | Stormwater Utility Fees | 2500000 | 7300000 | 0 | Carlos Rivera | Downtown District | 28.5418 | -81.3782 | -81.3782 | 28.5418 | Storm sewer capacity upgrades, detention, and inlet improvements. | 5 | 4 | 4 | 5 | 5 | 3 | Yes | Yes | Floodplain / Stormwater Standards | High-visibility project
CIP-0018 | Vehicle Fleet Electrification Phase 1 | Fleet / General Services | Fleet | Vehicles and Charging | design | Not Started | 3 | FY2028 | 2028-01-01 | 2032-12-31 | 6800000 | 180000 | Yes | State Energy Grant | General Fund | 1200000 | 5600000 | 0 | Amy Chen | All Departments | 28.5402 | -81.3711 | -81.3711 | 28.5402 | Replace light-duty fleet with EVs and install charging infrastructure. | 2 | 5 | 4 | 4 | 3 | 4 | Yes | Yes | State Clean Energy Program | Pilot phase
CIP-0019 | Detention Basin Rehabilitation – North Basin | Stormwater | Flood Control | Detention Basin | construction | Not Started | 4 | FY2029 | 2029-01-01 | 2031-12-31 | 3400000 | 90000 | Yes | General Fund | Stormwater Utility Fees | 0 | 3400000 | 0 | Carlos Rivera | North District | 28.6047 | -81.2705 | -81.2705 | 28.6047 | Regrade basin, repair outlet structure, and improve overflow protection. | 5 | 4 | 3 | 3 | 4 | 4 | Yes | Yes | Flood Mitigation Ordinance | Erosion control included
CIP-0020 | Library Branch Renovation and Expansion | Facilities Management | Buildings & Facilities | Public Building | construction | Not Started | 3 | FY2031 | 2031-01-01 | 2035-12-31 | 14500000 | 260000 | Yes | General Obligation Bond | State Cultural Grant | 3000000 | 11500000 | 0 | Patricia Moore | Central | 28.5514 | -81.3493 | -81.3493 | 28.5514 | Renovate and expand branch library for community use and accessibility. | 2 | 4 | 4 | 5 | 3 | 4 | Yes | Yes | Building Code / ADA / Fire Code | Includes community meeting space